## StatusList
Milestone | Priority | Task | Owner | Estimated Hours to Complete | Planned Start Date | Due Date | Status | What Tasks above must be completed before starting?
M3 | 1 | Create this project status tool | Tony | 0.16667 | 2017-04-06 | 2017-04-07 | Complete | NA
M3 | 3 | Setup Git Repo & upload directory/status tool created above | Tony | 0.16667 | 2017-04-06 | 2017-04-07 | Complete | NA | 2
M3 | 4 | Independently fill mapping worksheet | Tony & Robert | 3 | 2017-04-08 | 2017-04-12 | Complete | Setup Git Repo & upload directory/status tool created above | 3
M3 | 5 | Conference call to compare mappings & plan ETL | Tony & Robert | 2 | 2017-04-08 | 2017-04-12 | Complete | Independently fill mapping worksheet | 4
M3 | 6 | Install MS SQL suite and upload schema/data | Tony & Robert | 2 | 2017-04-13 | 2017-04-13 | Complete | NA
M3 | 7 | Write SQL queries for ETL | Tony & Robert | 5 | 2017-04-13 | 2017-04-18 | Complete | Install MS SQL suite and upload schema/data | 6
M3 | 8 | Create Data Tools package | Robert | 3 | 2017-04-19 | 2017-04-21 | Complete | Write SQL queries for ETL | 7
M3 | 9 | Test package | Robert | 1 | 2017-04-22 | 2017-04-22 | Complete | Create Data Tools package | 8
M3 | 10 | Finalize submission dir | Tony | 1 | 2017-04-25 | 2017-04-25 | Complete | NA